## Slide 1
CRITICAL PATH METHOD
St. Thomas College of Engineering and Technology
Name: Tanir Sahoo
University Roll No.: 12200121057
COMPUTER SCIENCE AND ENGINEERING
Subject : Software Engineering ESC-591
Date: 04.08.23
Class Roll No.: 61

## Slide 2
The Critical Path Method (CPM) is a powerful project management technique used to effectively plan, schedule, and manage complex projects. It provides a systematic approach to identify the most crucial tasks and their dependencies, allowing project managers to optimize the project timeline and allocate resources efficiently. At its core, CPM focuses on determining the critical path, which is the longest sequence of dependent activities in the project. The critical path represents the minimum time needed to complete the entire project, and any delays in activities along this path will directly impact the project's overall completion date. To implement CPM, project managers start by breaking down the project into individual activities, each with specific durations and dependencies. These activities are represented as nodes in a network diagram. The relationships between activities are defined, indicating which tasks must be completed before others can start. Through forward and backward pass calculations, CPM calculates the earliest and latest start and finish times for each activity. This allows project managers to identify the critical path and activities with slack or float time (activities that can be delayed without delaying the entire project). CPM's benefits are numerous. It helps identify potential bottlenecks and allows managers to focus their efforts on critical tasks, reducing the risk of project delays and cost overruns. It also aids in resource allocation, ensuring that resources are appropriately distributed to meet project deadlines. Moreover, CPM facilitates effective communication among team members and stakeholders, as it provides a clear roadmap of the project's timeline and priorities. If circumstances change during the project execution, managers can reevaluate the schedule and adjust accordingly to keep the project on track.
INTRODUCTION

## Slide 3
IDENTIFIER RESOLUTION
Symbol tables are used for identifier resolution by acting as a centralized repository of information about symbols (identifiers) encountered in the program source code. When the compiler or interpreter processes the code, it checks the symbol table to determine the properties and scope of each identifier, ensuring correct resolution. During compilation, as identifiers are encountered, the compiler looks them up in the symbol table. If the identifier is present, the compiler retrieves its attributes such as data type, memory location, and scope. This information is crucial for type checking, memory allocation, and scoping rules. If the identifier is not found in the symbol table, the compiler generates an error, indicating an undeclared symbol or a potential typo. Additionally, symbol tables prevent conflicts between identifiers with the same name but defined in different scopes.

## Slide 4
DEPENDENCIES
In the Critical Path Method (CPM), dependencies refer to the logical relationships between different project activities that determine their order of execution. Understanding these dependencies is crucial for constructing the project network diagram and identifying the critical path.
Finish-to-Star
Finish-to-Finish
Start-to-Start
Start-to-Finish
By defining these dependencies in the project network diagram, project managers can determine the sequence in which activities should be executed. Analyzing these relationships helps identify the critical path, allowing project teams to focus on the activities that directly impact the project's overall duration. Additionally, understanding dependencies enables effective scheduling, resource allocation, and risk management throughout the project lifecycle.

## Slide 5
NETWORK DIAGRAM
The Network Diagram is a graphical representation of the project's activities and their dependencies in the Critical Path Method (CPM). It provides a visual way to understand the sequence of activities and the relationships between them. The Network Diagram helps project managers and teams to identify the critical path, which is the longest path of dependent activities that determines the project's overall duration. In the Network Diagram, activities are represented as nodes or boxes, and the dependencies between them are depicted as arrows. The nodes represent the start and end points of each activity, while the arrows illustrate the logical relationships between activities, indicating which activity must be completed before the next one can start.
By analyzing the Network Diagram, project managers can identify the critical path, where activities have zero slack or float, meaning any delay in them will directly impact the project's completion time. Additionally, the diagram helps in visualizing the flow of work, highlighting potential bottlenecks, and assisting in resource allocation and schedule optimization.
Through the Network Diagram, project teams gain valuable insights into the project's structure, dependencies, and critical activities, allowing for better planning, coordination, and control of the project to ensure its successful and timely completion.

## Slide 6
FORWARD PASS
Forward Pass is the initial step in the Critical Path Method (CPM) used for project scheduling and determining the critical path.
It involves calculating the earliest possible start and finish times for each activity in the project network diagram.
The Forward Pass helps identify the critical path, which comprises activities with zero slack or float, indicating that any delay in these activities will directly impact the project's overall duration. Project managers use this information to prioritize critical activities and ensure the project's timely completion.
The process begins at the project's starting point with an early start time of zero and then progresses sequentially through the network, updating early start and early finish times for each activity based on its predecessors' information.

## Slide 7
BACKWARD PASS
Backward Pass is the second step in the Critical Path Method (CPM) used for project scheduling and determining the critical path.
It involves calculating the latest possible start and finish times for each activity in the project network diagram.
The Backward Pass helps identify the critical path by highlighting activities with zero slack or float. These are the activities that have the same early and late start times, indicating that any delay in them will directly impact the project's overall duration. Project managers use this information to focus on critical activities and manage resources effectively to ensure timely project completion.
The process begins at the project's ending point with a late finish time equal to the early finish time of the last activity. Then, it progresses backward through the network, updating late start and late finish times for each activity based on its successors' information.

## Slide 8
RESOURCE ALLOCATION
Resource allocation in the Critical Path Method (CPM) is the process of assigning the necessary resources, such as manpower, equipment, materials, and budget, to each activity within the project to ensure its successful completion while considering the critical path and project constraints.
1
Activity Durations
2
Resource Identification
3
Resource Availability
4
Resource Constraints
5
Critical Path Analysis
6
Resource Leveling
7
Resource Allocation
Techniques
8
Resource Smoothing
9
Resource Loading
10
Cost Considerations
11
Resource Allocation Matrix
12
Communication and
Collaboration
10
Flexibility
11
Trade-offs
12
Continuous Monitoring
Risk Management
10

## Slide 9
CONCLUSION
The Critical Path Method (CPM) is an invaluable project management tool that empowers project managers to plan, schedule, and execute complex projects with precision and efficiency. By breaking down the project into individual activities and analyzing their interdependencies, CPM identifies the critical path—the sequence of tasks that determine the shortest possible project duration. Understanding the critical path allows managers to focus their attention and resources on the most crucial activities, ensuring timely project completion. CPM provides numerous benefits, including improved project scheduling, resource allocation, and risk management. It enables project managers to identify potential bottlenecks and mitigate delays, leading to more successful project outcomes. The method also facilitates effective communication among team members and stakeholders, fostering collaboration and coordination.

## Slide 10
THANK YOU